## Slide 1
by
R. Y. Kadeer, Consultant (PAMD) & Former Joint Adviser
Project Appraisal & Management Division
Planning Commission
Government of India
Email: rkadeer@nic.in
Appraisal of Projects
1
Notes: 1

## Slide 2: Appraisal Structure
System of Project Appraisal is highly structured and institutionalized.
All Plan Schemes/projects pass through distinct phases with clearly laid down institutional mechanism.
A formal institutional set-up was established in 1972.
2
Notes: 2

## Slide 3: Public Investment Board (PIB)
PIB was set-up in 1972 in Ministry of Finance:
Examination of the broad contours of an investment proposal to prepare Feasibility Report
Taking investment decision on proposals for public investment
Consideration of proposals for revision in cost estimates.
3

## Slide 4
PAD was set up in 1972 in Planning Commission to:
  Develop formats & guidelines for the submission of proposals for the projects/programs.
  Undertake support studies for improving appraisal methodology and procedures.
  Undertake the techno economic appraisal of major projects and programs in the public sector.
  Assist Central Ministries in establishing proper procedures for preparation of Feasibility Reports.
Project Appraisal Division (PAD)
4

## Slide 5
Appraising Agencies
Planning Commission
Project Appraisal & Management Division
Department of Expenditure
Ministry of Environment & Forests
Plan Finance (II)
Environment Impact Assessment (EIA)Division
5

## Slide 6: Appraisal by PAMD
EFC/PIB Plan Proposals Costing Rs. 100 Crores and above.
New and Revised Cost Proposals.
Railway Projects Costing Rs. 300 Cr. and above.
Proposals of Ministry of Defense, Deptt. Of Atomic Energy and Space are exempted from PIB/EFC.
Projects of Navaratna Companies are not appraised by PAMD.
6

## Slide 7
Forum for Appraisal
Cost of Project/Scheme | System of Appraisal
< Rs. 25 Cr. | Ministry/Department concerned, in normal course
> Rs. 25 Cr. & < Rs.100 Cr. | SFC chaired by the Secretary of the Department concerned.
>Rs.100 Cr. & < Rs.300 Cr. | EFC Chaired by the Secretary of the concerned Ministry/Department.
> Rs.300 crore | PIB/EFC Chaired by Secretary, Department of Expenditure
**Projects /Schemes where financial returns are quantifiable are to be considered by PIB and others by EFC
7

## Slide 8
8
Secretary of Administrative Ministry
Approval Authority
Minister in-charge of Administrative Ministry
Minister of Adm. Ministry & Finance Minister.
Cabinet/CCEA
Cabinet/CCEA (Irrespective of Cost)
Authority for Approval
8
Financial limits Rs. cr.
<25
= 25 & <150
>150 & <300
=>300
New autonomous bodies

## Slide 9: Investment Decision Stages
Identification of New Project/Scheme
IPA from Secretary (PC) for new scheme in Plan
Circulation of EFC/PIB Memo by Ministry
Appraisal by PAMD (PC)
Recommendation by EFC/PIB
Full PC Approval for new CSS
Approval by CCEA/Cabinet
9

## Slide 10
10
Process | Time
Decision on ‘in principle’ approval | 4 weeks
Preparation of DPR and its circulation | Varies from Project to Project
Appraisal of DPR & draft EFC/PIB memo by Appraisal agencies | 4 weeks
Circulation of Final EFC/PIB Memo | 1 week
EFC/PIB meeting after final EFC/PIB memo | 4 weeks
Issue of the minutes of EFC / PIB | 1 week
Submission for approval of Adm. Minister & FM (for projects of >Rs. 150 cr & < Rs. 300 cr) | 2 weeks
Sub. to Cabinet/CCEA for approval (>Rs. 300 cr) | 4 weeks
Time Frame for Appraisal & Approval
10

## Slide 11
Need and justification
Design & Technological aspects
Implementation & Monitoring Mechanism
Plan Provision and Financing Arrangement
Reliability of Cost Estimates
Financial/Commercial Viability
Economic Viability
Environmental Aspects
Risk/Sensitivity Analysis
Project Appraisal Aspects
11

## Slide 12
Project Formulation
Identification & Objective
Type of Scheme-CS or CSS
Description, location, area, population coverage
New or Ongoing Scheme –Impact
Objectives- as related to Govt. policy, Plan
Convergence with other schemes
Outputs & Outcomes
12

## Slide 13: Need & Justification
National Policy framework
Demand Analysis to identify gaps
Existing facilities /services
Examination of Alternatives- physical & financial
Duplication/overlapping to be avoided

## Slide 14: Scope & Design
Scope of scheme is defined
Identification of target area/population/beneficiaries.
Selection criteria of target groups/area etc.
Physical parameters/components to be described
Phasing of targets matching with financial outlay
Delivery mechanism of goods/services
Technical aspects –machinery, equipment

## Slide 15: Implementation & Monitoring
Implementing Agency to be identified
Capability of Implementing Agency
Implementation structure
Implementation Schedule- activity-wise
Manpower- Requirement, type, new creation etc.
Monitoring Mechanism –QPR
Nodal Officer- Overall responsibility of monitoring
Provision for concurrent evaluation
Management information system (MIS)

## Slide 16: Plan Provision and Funding
It should be included in the FYP/AP
Phasing of expenditure- matching with physical targets
Adequate Plan Provision /funding arrangement
Sources of funding- GBS, IEBR, Loans etc.
Funding Modalities- Sharing, Releases,
Funds utilization – Certificates, audits etc.

## Slide 17: Cost Estimates
Total cost of the scheme irrespective of sources
Item-wise break-up –recurring & non-recurring costs
Basis of estimates- quotations, market price etc.
Reference date /price level of estimates (< 6 month)
Estimates on constant price level
Quantities, rates to be used to arrive at estimates.
Financial Assistance Norms/pattern

## Slide 18: Benefit Cost Analysis
Whether benefits are quantifiable in monetary term?
If so, costs and benefits should be quantified & Valued in Financial and economic terms.
Cash flows in financial & economic terms should be prepared.
Financial & Economic Internal Rate of Return to be calculated to establish viability as per Govt norms.
Net Present Value be calculated at prescribed discount rate- if it is positive, project is viable.
If benefits are not quantifiable in monetary term, tangible and intangible benefits should be quantified & indicated along with sustainability.

## Slide 19: Environmental Impacts
Environmental Impact Assessment
Quantification and valuation of environmental impacts
Environment protection /restoration measures
Rehabilitation & Resettlement Plan
Cost associated with environment & forest protection
Obtaining environment and forest clearances
Some External impacts
Power Plant: Air pollution- health hazards to people around
Irrigation Project: Siltation, soil salinization- , adverse effect on
agricultural yields, farm income
Industrial Plant- Waste discharge into river- loss of fish production lower income of fishermen

## Slide 20: Risk & Sensitivity Analysis
Probable Risk factors to be identified and indicated
Risk mitigation measures suggested
Sensitivity analysis to be carried out by altering inflows and outflows of the project, impact of delay, less production etc. to identify variables to which project is most sensitive.

## Slide 21
Financial Viability Analysis
Cash Flow Preparation
Valuation of inputs and outputs at market price
Valuation of imported items at market rates of foreign exchange- landed cost at site.
Cash flows are to be prepared at constant prices
Viability to be calculated on completion cost basis.
Risk/Sensitivity Analysis.
21

## Slide 22
Economic Viability Analysis
Cash flow Preparation
Valuation of Traded inputs and outputs at border prices (CIF/FOB).
Valuation of non-traded goods and services at marginal cost of their production or at opportunity cost (net off taxes & duties, subsidies etc.)
Premium of FE cost is taken (20% at present).
Externalities, secondary /indirect effects are identified and monetized.
System and sunk costs are accounted for.
22

## Slide 23
Criteria for Investment Decision
Project type | FIRR | EIRR
Normal Projects | >12 % | >12 %
Railway | >14 % | >14 %
Core Sector/Strategic Importance | Reasons to be detailed | Reasons to be detailed
Mutually Exclusive Projects | Higher NPV | Higher NPV
23

## Slide 24
Appraisal of Social Sector Schemes
In confirmity with National policy
Identification of Targets/Population/Areas
Convergence to avoid Duplication
Examination of Alternatives through Least Cost method
Inclusion of Scheme in Five year/Annual Plans with adequate outlays
24

## Slide 25
Sensitivity Analysis
Take care of Uncertainties
Take Care of Time over-run
Take Care of Profitability
Take Care of Capacity Utilization
Take Care of Price Fluctuations
Set up relation between the underlying basic factor and NPV
Estimate Range of Variation
Compute the impact of Variation in each Variable on NPV
25

## Slide 26
Viability Indicators for Analysis
FIRR
EIRR
NPV
UCP
BCR
Payback Period
26

## Slide 27
Appraisal Aspects of RCE
Present Status of Project- Physical & Financial
Plan Outlays and Funding status
Cost Variance analysis
  Between revised cost and latest approved cost
  Comparison – item-wise
Factors attributed to cost variation:
  Price escalations- Indigenous and FE component
  Exchange rate variations
  Statutory duties
  Scope Change/additions/deletions/underestimation
  Other reasons
Proposals for Revised Cost Estimates
27

## Slide 28
Appraisal Aspects of RCE contd…
Analysis of Time overrun
  Cost overrun due to time overrun
  Reasons of Time overrun
  Variance within approved PTC and beyond
  Fixing responsibility for time and cost over-run by Standing Committee.
Viability analysis
Impact of Cost and Time overruns on Economic and Financial Viability, Cost of production & generation etc.
Proposals for Revised Cost Estimates
28

## Slide 29
Standing Finance Committee (SFC)
(>25 cr & <100 cr.)
Secretary of Administrative Ministry/Deptt. -Chairperson
Financial Advisor of Admin. Ministry -Member
Joint Secretary in Charge of Admin Min. -Member
Representative of the Planning Commission, Department of Expenditure and any other Ministry/Department that the Secretary/Financial Advisor may suggest can also be invited, as
per requirement.

## Slide 30
Expenditure Finance Committee (EFC)
(For proposals costing >100 cr. & <300 crore)
Secretary of Admin. Ministry/Deptt. -Chairman
Secretary, Planning Commission or his repres. -Member
Secretary Deptt. of Expenditure) or his repres. -Member
Financial Advisor of Administrative Ministry -Member-Secretary

## Slide 31
Composition of EFC (Main)
(Proposal costing 300 cr. & above)
Secretary, Department of Expenditure -Chairman
Secretary, Planning Commission or his repres. -Member
Secretary of the Administrative Ministry -Member
Financial Advisor of Admin. Ministry -Member-Secretary

## Slide 32
Public Investment Board (PIB)
Secretary, Deptt. of Expenditure -Chairman
Secretary ,Planning Commission) -Member
Secretary, Min. of Statistics & Progra. Impl. - Member
Secretary, Min. of Environment & Forests) -Member
Secretary of Admin. Ministry -Member
Secretary, Deptt. of Economic Affairs -Member
Joint Secretary (PF.II), Deptt. of Expenditure -Member -
Secretary

## Slide 33
Thank You
33
Cost Effectiveness Analysis of Water Supply Project (Fig: in Rs.) |  |  |  |  |  | 
Discount Rate 12% | Alternative A |  |  | Alternative B |  | 
Year | 0 | 1- 24 | 25 | 0 | 1- 24 | 25
Installation Cost | 90000 | 0 | -15000 | 70000 | 0 | 0
O&M Cost |  | 20000 |  |  | 22500 | 
Total Cost | 90000 | 20000 | -15000 | 70000 | 22500 | 0
NPV ot Total Cost | 219,625 |  |  | 240,152 |  | 
Alternative A is cost effective, hence should be selected |  |  |  |  |  | 

## Slide 34
Captive Power Plant (1320 MW)at Adra by JVC -NTPC & Railways |  |  |  |  |  |  |  |  | 
 |  | Financial Viability |  |  |  | Figs. in crore |  |  | 
Year | Cap Cost | Fuel Cost | O&M | Int on WC | Total Outflow | Energy kwh | Tariff Rs.) | Inflow | Net Flow
1 | 694.75 | 0 | 0 | 0 | 694.75 | 0 |  | 0 | -694.75
2 | 1042.12 | 0 | 0 | 0 | 1042.12 | 0 |  | 0 | -1042.12
3 | 4029.55 | 0 | 0 | 0 | 4029.55 | 0 |  | 0 | -4029.55
4 | 1181.07 | 0 | 0 | 0 | 1181.07 | 0 |  | 0 | -1181.07
5 | 0 | 428.30 | 64.98 | 22.29 | 515.57 | 601.19 | 2.29 | 1376.73 | 861.16
6 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
7 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
8 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
9 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
10 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
11 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
12 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
13 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
14 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
15 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
16 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
17 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
18 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
19 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
20 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
21 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
22 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
23 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
24 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
25 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
26 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
27 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
28 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
29 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
SV 10% | -654.65 | 0.000 | 0 | 0 | -654.65 | 0 | 0 | 0.00 | 654.65
NPV 12% |  |  |  |  | 9185.154 | 4313.499 |  | 11546.307 | 2361.153
 | Cost of Generation at 12% discount |  |  |  | 2.13 |  |  | FIRR | 17.0%
Assumptions |  |  |  |  |  |  |  |  | 
All figures on constant price level |  |  |  |  |  |  |  |  | 
Salvage Value of capital asset is taken at 10% of capital cost excluding land cost |  |  |  |  |  |  |  |  | 
Energy generation at 85% PLF |  |  |  |  |  |  |  |  | 

## Slide 35
Captive Power Plant (1320 MW)at Adra by JVC -NTPC & Railways |  |  |  |  |  |  |  |  | 
 |  | Economic Viability |  |  |  | Figs. in crore |  |  | 
Year | Cap Cost | Fuel Cost | O&M | Int on WC | Outflow | Energy kwh | Tariff Rs.) | Inflow | Net Flow
1 | 661.15 | 0 | 0 | 0 | 661.15 | 0 |  | 0 | -661.15
2 | 991.72 | 0 | 0 | 0 | 991.72 | 0 |  | 0 | -991.72
3 | 3834.66 | 0 | 0 | 0 | 3834.66 | 0 |  | 0 | -3834.66
4 | 1123.95 | 0 | 0 | 0 | 1123.95 | 0 |  | 0 | -1123.95
5 | 0 | 428.30 | 64.98 | 22.29 | 515.57 | 601.19 | 2.29 | 1376.73 | 861.16
6 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
7 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
8 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
9 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
10 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
11 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
12 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
13 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
14 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
15 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
16 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
17 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
18 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
19 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
20 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
21 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
22 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
23 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
24 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
25 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
26 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
27 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
28 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
29 | 0 | 666.90 | 163.27 | 40.24 | 870.41 | 899.33 | 2.71 | 2437.18 | 1566.77
SV 10% | -654.65 | 0.000 | 0 | 0 | -654.65 | 0 | 0 | 0.00 | 654.65
NPV 12% |  |  |  |  | 8939.96 | 4313.50 |  | 11546.31 | 2606.35
 | Cost of Generation at 12% discount |  |  |  | 2.07 |  |  | EIRR | 17.7%
Assumptions |  |  |  |  |  |  |  |  | 
All figures on constant price level |  |  |  |  |  |  |  |  | 
Salvage Value of capital asset is taken at 10% of capital cost |  |  |  |  |  |  |  |  | 
Capital cost net off taxes & duties considering mega project benfits |  |  |  |  |  |  |  |  | 
Energy generation at 85% PLF |  |  |  |  |  |  |  |  | 

## Slide 36
Thank You
36